## Sheet1
Production Schedule | Time Start | Time End | Done | Bugs Fixed | Cant do
Design Characters | 11th Feb | 28th Feb |  |  | Started
Design Environments | 22nd April | 1st May |  |  | Done
Research Sounds | 11th Feb | 28th Feb
Record Sounds | 11th Feb | 28th Feb
Create Assets | 11th Feb | 1st May
Photograph/Documentation | 11th Feb | 15th May
Build Prototype (No Art) | 11th Feb | 11th Feb
Build Prototype (With Art) | 11th Feb | 22nd April
Plan Behaviours of Objects | 11th Feb | 22nd March
Concept HUD/GUI | 11th Feb | 1st March
Finished Model | 11th Feb | 1st May
Fix Final Bugs | 1st May | 15th May
Build Alpha | 15th May | 3rd June